## July-Aug 2024
Date | Tasks | Status | Remarks
Basic introduction to Project and General Discussion:Build an Online Learning Platform that allows users to:Access interactive video lectures, assignments, and quizzes.Track progress through completion stats and leaderboards. Support features like adding PDFs, images, and videos as course chapters. Provide personalized dashboards for users to monitor their performance and achievements.Include social engagement through forums or peer discussions. The platform will focus on user-friendly design, seamless interactivity, and scalability.
2024-09-08 | KT,introduction | Completed | NA
2024-09-10 | Task Title: Implement Completion Stats UI for Front-End Bootcamp Progress Tracking | Completed | NA
2024-09-11 | Develop a UI component to display user progress stats for the Front-End Bootcamp. The component should include: | Completed | NA
2024-09-12 | Detailed Table: A breakdown of lectures with fields such as "Lecture Name," "Videos Watched," and "Progress Percentage." | Completed | NA
2024-09-13 | Make completion stats ui responsive for all formats | Completed
2024-09-14 | Implement Prgress bar depending upon scrore in give assignment of lecture | Completed | NA
2024-09-15 | Create the leaderboard table structure as provided in UI.Add participant details (e.g., name, rank, score, badge, institution). | Completed | NA
2024-09-18 | Header and Navigation :Implement the header section, including the league progression bar. | Completed | NA
2024-09-19 | Weekly Status Cards: Design the "Active Week Status" and "Last Week Status" cards. | Completed | NA
2024-09-20 | Dynamically render data (e.g., rank, score, league name)./Debugging | Completed | NA
2024-09-21 | Weekly Task review | Completed
2024-09-22 | Leaderboard Section:Create the leaderboard table structure.Add participant details (e.g., name, rank, score, badge, institution). | Completed | NA
2024-09-25 | State Management:Implement state management using Context API or Redux for dynamic data flow.Add mock data for testing components. | Completed | NA
2024-09-26 | Interactivity :Add interactivity, such as hover effects and tooltips.Ensure responsiveness for mobile and desktop views. | Completed | NA
2024-09-27 | Testing and Bug Fixes ,Create APIs for:Fetching leaderboard data.Fetching weekly status (active and last week). | Completed | NA
2024-09-28 | User Authentication (Optional)Implement user authentication to show personalized data (e.g., "See yourself on leaderboard").Set up secure API endpoints. | Completed | NA
2024-09-29 | Weekly Task review ,Optimize the front-end for production (e.g., minify assets, lazy load components). | Completed