## July-Aug 2024
Date | Tasks | Status | Remarks
2024-07-15 | Developing Skill Badges and Doubt page UI | Completed | NA
1/1/2025 | Create a static UI for the Skill Badges Page | Completed | NA
3/1/2025 | Integrate it with routing and perform testing with Mock data | Completed | NA
2025-06-01 | Dynamic Data Integration | Completed | NA
2025-08-01 | Filter and Search for Skill Badges as per Moules | Completed | NA
2025-09-01 | Add a search bar to search for badges or modules. Ensure the badges page works well on mobile, tablet, and desktop screens. | Completed
2025-10-01 | Weekly Task review | Completed | NA
13/1/2025 | Build the booking Sessions page UI. | Completed | NA
14/1/2025 | Implement a form for scheduling mock interviews. | Completed | NA
15/25/2025 | Form for Scheduling Interviews:Create a form with the following fields(Name,Email,Date) | Completed | NA
15/26/2025 | Validate user inputs (e.g., required fields, date selection). | Completed | NA
16/1/2025 | KT (Mongo db aggregation pipeline) | Completed
17/1/2025 | Weekly Task review | Completed | NA
20/1/2025 | Develop Show a confirmation message page after booking | Completed | NA
21/1/2025 | Use local storage or mock backend to save the scheduled interviews. | Completed | NA
22/1/2025 | Post this data to backend with Redux | Completed | NA
23/1/2025 | Perform unit testing ,and also integrate this pages though routing, ensure all pages in media friendly manner | Completed | NA
24/1/2025 | Weekly Task review | Completed
27/1/2025 | Create a static UI for the candidates Doubt repository Page | Completed | NA
28/1/2025 | Implement serarch and filter functionality to display them module wise | Completed | NA
29/1/2025 | KT | Completed | NA
30/1/2025 | Perform unit testing ,and also integrate this pages though routing, ensure all pages in media friendly manner | Completed | NA
31/1/2025 | Weekly Task review | Completed | NA
|  | Completed | NA