## July-Aug 2024
Date | Tasks | Status | Remarks
2024-07-15 | Basic introduction to Project and General Discussion | Completed | NA
2024-07-16 | Integration of Sign up page | Completed | NA
2024-07-17 | UI development of Signup and Login pages using React components, focusing on user-friendly UI and responsive design. | Completed | NA
2024-07-18 | Implement form validation for the signup and login forms. | Completed | NA
2024-07-19 | Set up routing between the signup, login, and home pages using React Router. | Completed | NA
2024-07-20 | Weekly Task review | Completed
2024-07-22 | Create a User model in MongoDB to store user data (name, email, hashed password). | Completed | NA
2024-07-23 | Implement password hashing using bcrypt for secure user registration. | Completed | NA
2024-07-24 | Implement a Login API route that checks credentials against the database. | Completed | NA
2024-07-25 | Set up JWT (JSON Web Tokens) for user authentication, including token generation and validation | Completed | NA
2024-07-26 | Implement error handling for both registration and login routes (e.g., user already exists, wrong password). | Completed | NA
2024-07-27 | Weekly Task review | Completed
2024-07-29 | Connect the Signup page to the backend API to send user data and register. | Completed | NA
2024-07-30 | Create a Login page and integrate it with the backend to authenticate users. | Completed | NA
2024-07-31 | Authentication and Authorization:Implement protected routes using React Router (e.g., if a user is not logged in, redirect to the login page). | Completed | NA
2024-08-01 | Display appropriate user status (logged in or logged out) on the homepage.Implement local storage or cookies to store the JWT token on the frontend and pass it with requests.Create a logout functionality to clear the stored token and redirect to the login page. | Completed | NA
2024-08-02 | Implement middleware for JWT authentication to protect API routes that require login.Set up token validation and user session management. | Completed | NA
2024-08-03 | Weekly Task review | Completed
2024-08-05 | Implement final UI/UX improvements and ensure the signup, login, and home pages are functioning smoothly.est the entire flow from signup to login and protected routes. | Completed | NA
2024-08-06 | Conduct responsive design testing to ensure compatibility on various screen sizes. | Completed | NA
2024-08-07 | Conduct thorough testing of API endpoints to ensure they function as expected (e.g., registration, login, token validation).Ensure MongoDB is storing user data securely and that JWT tokens are being correctly generated and verified. | Completed | NA
2024-08-08 | Final code review and cleanup of the repository.Deploy the final codebase to a live server and ensure the frontend is connected to the live backend. | Completed | NA
2024-08-09 | Update the project README with setup instructions, API documentation, and any other relevant information. | Completed | NA
2024-08-10 | Weekly Task review | Completed | NA